## Project Management
Net Neutrality Project Management
Components | Details | Leader | Live? | Status | Due Date | Completion Date
Website | Site Selection: determine best option | All | Yes | Completed | 2014-10-20 | 10/2/14
| Structure: determine layout, pages, and organization | MG & JH | Yes | Completed | 2014-10-20 | 10/2/14
| Titles: determine page titles | All | Yes | Completed | 2014-10-20 | 10/2/14
| Image(s): select and cite images on site | MG | Yes | Completed | 2014-10-20 | 10/2/14
| Table of contents: ensure links work and are organized | MG | Yes | Completed | 2014-10-20 | 10/2/14
| Abstract: create/revise | JH | Yes | Completed | 2014-10-20 | 10/13/14
| Group bio, instructor, and date | LK | Yes | Completed | 2014-10-20 | 10/2/14
Summaries | Background and technology | LK | Yes | Completed | 2014-12-07 | 12/1/14
| Recent developments | CW | Yes | Completed | 2014-12-07 | 12/1/14
| Future trends | MG | Yes | Completed | 2014-12-07 | 12/1/14
| Future impact | JH | Yes | Completed | 2014-12-07 | 12/3/14
| Social implications | All |  | Completed | 2014-12-07 | 12/4/14
Site editing: all sections above must be completed
Project Mgmt | Schedule group meetings | JH | N/A | Completed | N/A
| Meeting agendas: delegate responsibilites | All | N/A | Completed | N/A
| Meeting chats | JH | N/A | Completed | N/A
| Meeting minutes | LK | Yes | Completed | N/A
| Spreadsheet | MG/All | Yes | Completed | 2014-12-07 | 12/7/14
References | list #1: all members must submit work before submission | CW & LK | Yes | Completed | 2014-09-22 | 9/21/14
| list #2: all members must submit work before submission | CW |  |  | 2014-11-10 | 11/09/14
| summaries: lists must be compiled prior to completion | All | Yes | Ongoing | 2014-12-07
Reference Maintenance | Statement of sources, criteria for inclusion | LK & JH | Yes | Completed | N/A | 10/6/14
| Link/URL maintenance | CW | Yes | Ongoing | 2014-12-07
| Categorization: complete summaries prior to organization | All | Yes | Completed | N/A | 10/12/14
Summary & Assessment | Challenges |  |  |  | 2014-12-07
| Benefits |  |  |  | 2014-12-07
| Future application |  |  |  | 2014-12-07
Collaborative Evaluation | Rationale |  |  |  | 2014-12-07
| Description |  |  |  | 2014-12-07
| Templates |  |  |  | 2014-12-07
| Results |  |  |  | 2014-12-07
| Interpretation |  |  |  | 2014-12-07
| Conclusion |  |  |  | 2014-12-07
Assessments | Peer assessments | All | N/A | N/A | 2014-12-07 | N/A